## Report
OST Project
Earned Value Analysis Report
| Prepared By: | James Dumitru
| Date: | 2020-04-22
[42]
| For Period: | 2020-04-29
Summary:
This Planned Value is for providing a cost towards buyers who would like to invest in our cost of work towards a web crawler.
This is for each person
[15 empty] | Roles: | Price per hour:
Planned Value (PV) or Budgeted Cost of Work Scheduled (BCWS) | [6 empty] | WEEKS | [7 empty] | Project Manager | 80
WBS | Task Name | TBC | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Software Developer | 50
1 | OSINT | [13 empty] | Software Developer | 50
1.1 | Planning Phase | [13 empty] | Software Developer | 50
1.1.1 | Process Requirements | 700 | 350 | 350 | [10 empty] | Data Analyst | 40
1.1.2 | Data Requirements | 1000 | 500 | 500 | [10 empty] | Data Analyst | 40
1.1.2.1 | Identifying Roles | 500 | 500
1.1.3 | Design Requirements | 1000 | 500 | 500
1.2 | Execution Phase
1.2.1 | Begin Software Development | 4500 |  |  | 1500 | 1500 | 1500
1.2.2 | Begin Code Development | 3000 |  |  |  | 1500 | 1500
1.2.3 | Test Code | 2000 | [5 empty] | 1000 | 1000
1.2.4 | Debug | 6400 | [6 empty] | 1400 | 1000 | 1000 | 1000 | 1000 | 1000
1.3 | Monitoring and Controlling Phase
1.3.1 | Review Requirements for UI | 1000 | [7 empty] | 500 |  |  | 500
1.3.2 | Draft Design | 800 | [7 empty] | 800
1.3.3 | Begin UI Development | 2000 | [7 empty] | 1000 | 1000
1.3.4 | Test UI | 2400 | [8 empty] | 800 | 800 | 800
1.4 | Project Closeout Phase
1.4.1 | Integrate with code | 6000 | [9 empty] | 2000 | 2000 | 2000
1.4.2 | Data Analysis | 2600 | [10 empty] | 1500 | 1100
1.4.3 | Requirements Checklist | 600 | [10 empty] | 300 | 300
1.4.4 | Final Deliverables | 1000 | [10 empty] | 500 | 500
1.4.5 | Final Review | 2000 | [10 empty] | 1000 | 1000
1.4.6 | Complete report/Presentation | 2000 | [10 empty] | 1000 | 1000
Insert new rows above this one
| Total Budgeted Cost | 25300 | 1850 | 1350 | 1500 | 3000 | 3000 | 1000 | 2400 | 3300 | 2800 | 3800 | 8600 | 6900
|  | Cumulative Planned Value (PV) | 1850 | 3200 | 4700 | 7700 | 10700 | 11700 | 14100 | 17400 | 20200 | 24000 | 32600 | 39500
Actual Cost and Earned Value
|  | Cumulative Actual Cost (AC) | 3550 | 5150 | 9950 | 14750 | 19550 | 21950 | 26750 | 29150 | 35230 | 37630 | 47350 | 64760
|  | Cumulative Earned Value (EV) | 2500 | 6375 | 6750 | 7125 | 9500 | 2640 | 9200 | 6400 | 7260 | 7560 | 8670 | 16230
Project Performance Metrics
|  | Cost Variance (CV = EV - AC) | -1050 | 1225 | -3200 | -7625 | -10050 | -19310 | -17550 | -22750 | -27970 | -30070 | -38680 | -48530
|  | Schedule Variance (SV = EV - PV) | 650 | 3175 | 2050 | -575 | -1200 | -9060 | -4900 | -11000 | -12940 | -16440 | -23930 | -23270
|  | Cost Performance Index (CPI = EV/AC) | 0.70423 | 1.2379 | 0.67839 | 0.48305 | 0.48593 | 0.12027 | 0.34393 | 0.21955 | 0.20607 | 0.2009 | 0.1831 | 0.25062
|  | Schedule Performance Index (SPI = EV/PV) | 1.3514 | 1.9922 | 1.4362 | 0.92532 | 0.88785 | 0.22564 | 0.65248 | 0.36782 | 0.35941 | 0.315 | 0.26595 | 0.41089
|  | Estimated Cost at Completion (EAC) | 35926 | 20438.4314 | 37294.0741 | 52375.4386 | 52064.7368 | 210354.1667 | 73562.5 | 115233.5938 | 122771.2121 | 125931.0847 | 138172.4337 | 100950.5853

## EV
Earned Value Worksheet
This worksheet is used to help calculate the Earned Value (EV) or Budgeted Cost of Work Performed (BCWP). | [14 empty] | Earned Value Management Template
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet. | [14 empty] | © 2012 Vertex42 LLC
Enter the % Complete for each task to calculate the cumulative earned value.
Cumulative Earned Value (EV)
WBS | Task Name | TBC | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1 | OSINT | -
1.1 | Planning Phase | -
1.1.1 | Process Requirements | 700
1.1.2 | Data Requirements | 1000 | 100%
1.1.2.1 | Identifying Roles | 500 | 100% | [9 empty] | 100%
1.1.3 | Design Requirements | 1000 | 100%
1.2 | Execution Phase
1.2.1 | Begin Software Development | 4500 |  | 85% | 90% | 95% | 100%
1.2.2 | Begin Code Development | 3000 |  | 85% | 90% | 95% | 100%
1.2.3 | Test Code | 2000 |  |  |  |  | 100% | 100% | 100%
1.2.4 | Debug | 6400 | [6 empty] | 100% | 100%
1.3 | Monitoring and Controlling Phase | [14 empty] | This is for each person
1.3.1 | Review Requirements for UI | 1000 | [13 empty] | Roles: | Price per hour:
1.3.2 | Draft Design | 800 | [5 empty] | 80% | 100% | [6 empty] | Project Manager | 80
1.3.3 | Begin UI Development | 2000 | [13 empty] | Software Developer | 50
1.3.4 | Test UI | 2400 | [8 empty] | 90% | 90% |  | 95% |  | Software Developer | 50
1.4 | Project Closeout Phase | [14 empty] | Data Analyst | 40
1.4.1 | Integrate with code | 6000 | [8 empty] | 85% | 90% | 95% | 98% |  | Data Analyst | 40
1.4.2 | Data Analysis | 2600 | [10 empty] | 95% | 95%
1.4.3 | Requirements Checklist | 600 | [11 empty] | 100%
1.4.4 | Final Deliverables | 1000 | [11 empty] | 100%
1.4.5 | Final Review | 2000 | [11 empty] | 100%
1.4.6 | Complete report/Presentation | 2000 | [11 empty] | 100%
Insert new rows above this one
|  | Cumulative EV | 2500 | 6375 | 6750 | 7125 | 9500 | 2640 | 9200 | 6400 | 7260 | 7560 | 8670 | 16230

## AC
Actual Cost Worksheet
Use this worksheet to help calculate the Actual Cost (AC) of Work Performed (ACWP) by entering the costs incurred each period.
Make sure that the WBS, Task Name, and TBC are identical to the table in the Report worksheet.
Transfer the Cumulative Actual Cost to the Report worksheet.
Actual Cost (AC) of Work Performed
WBS | Task Name |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
1 | OSINT
1.1 | Planning Phase
1.1.1 | Process Requirements |  | Wk 1: 800; Wk 2: 800; Wk 12: 800
1.1.2 | Data Requirements |  | Wk 1: 800; Wk 2: 800; Wk 12: 800
1.1.2.1 | Identifying Roles |  | Wk 1: 800
1.1.3 | Design Requirements |  | Wk 1: 1150; Wk 12: 1150
1.2 | Execution Phase
1.2 | Execution Phase |  | Wk 3: 2400; Wk 4: 2400; Wk 5: 2400
1.2.1 | Begin Software Development |  | Wk 3: 2400; Wk 4: 2400; Wk 5: 2400
1.2.2 | Begin Code Development |  | Wk 6: 2400; Wk 7: 2400
1.2.3 | Test Code |  | Wk 7: 2400; Wk 8: 2400
1.2.4 | Debug
1.3 | Monitoring and Controlling Phase |  | Wk 9: 1840 | This is for each person
1.3.1 | Review Requirements for UI |  | Wk 9: 1840; Wk 12: 1840 | Roles: | Price per hour:
1.3.2 | Draft Design |  | Wk 9: 2400 | Project Manager | 80
1.3.3 | Begin UI Development |  | Wk 10: 2400 | Software Developer | 50
1.3.4 | Test UI |  | Wk 11: 1840; Wk 12: 1840 | Software Developer | 50
1.4 | Project Closeout Phase | [13 empty] | Software Developer | 50
1.4.2 | Data Analysis |  | Wk 11: 1040; Wk 12: 1040 | Data Analyst | 40
1.4.3 | Requirements Checklist |  | Wk 11: 640; Wk 12: 640 | Data Analyst | 40
1.4.4 | Final Deliverables |  | Wk 11: 3100; Wk 12: 3100
1.4.5 | Final Review |  | Wk 11: 3100; Wk 12: 3100
1.4.6 | Complete report/Presentation |  | Wk 12: 3100
Insert new rows above this one
|  | Total Actual Cost | 3550 | 1600 | 4800 | 4800 | 4800 | 2400 | 4800 | 2400 | 6080 | 2400 | 9720 | 17410
|  | Cumulative Actual Cost (AC) | 3550 | 5150 | 9950 | 14750 | 19550 | 21950 | 26750 | 29150 | 35230 | 37630 | 47350 | 64760