## Instructions
RISK MANAGEMENT LOG
Column | Instructions For Completing This Document
Complete the Project Name, NC, Project Manager Name, and Project Description fields
For each risk identified, complete the following:
A | ID: A unique ID number used to identify the risk in the risk tracking log.
B | Current Status: This column should be populated with the risk's current status. o Open: The risk is currently open but is not yet an issue. o Closed: The risk is no longer considered an active project threat and can be closed with or without resolution.
C | Risk Impact: This column should be populated with the potential impact of the risk if it did become a project issue. Valid options include the following: High, Medium, Low. These are defined as follows: o High: Risk that has the potential to greatly impact project cost, project schedule or performance. o Medium: Risk that has the potential to slightly impact project cost, project schedule or performance. o Low: Risk that has relatively little impact on cost, schedule or performance.
D | Probability of Occurrence: This column should be populated with the estimated probability that the risk will at some point become a project issue.
E | Risk Map: This is a calculated field based on the values selected for both Risk Impact and Probability of Occurrence. o Green: LL (Low Probability, Low Impact), LM (Low Probability, Medium Impact), ML (Medium Probability, Low Impact) o Yellow: LH (Low Probability, High Impact), MM (Medium Probability, Medium Impact), HL (High Probability, Low Impact) o Red: MH (Medium Probability, High Impact), HM (High Probability Medium Impact), HH (High Probability, High Impact)
F | Risk Description: This column should be populated with a description of the risk.
G | Project Impact: This column should be populated with a description of the potential project impact as a result of the risk.
H | Risk Area: This column should be populated with the appropriate risk area.
I | Symptoms: This column should be populated with the symptoms of risk that may eventually lead to the execution of a risk contingency plan.
J | Trigger: This column should be populated with the triggers that would indicate the requirement to execute contingency plans.
K | Risk Response Strategy: This column should be populated with the preferred risk response strategy.
L | Response Strategy: This column should be populated an appropriate response strategy to prevent the risk from becoming an issue.
M | Contingency Plan: This column should be populated with a description of the risk contingency plan.
Column | Instructions For Changing the Contents of Drop-Down Menus
C, D, H | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## Risk_Tracking_Log
RISK MANAGEMENT LOG | [7 empty] | RISK MANAGEMENT LOG
Project Name: |  |  | <OS INT Final > |  |  |  |  | Project Name: | <OS INT Final >
National Center: |  |  | <OSINT> |  |  |  |  | National Center: | <OSINT>
Project Manager Name: |  |  | <James Dumitru> |  |  |  |  | Project Manager Name: | <James Dumitru>
Project Description: |  |  | <Web Crawler> |  |  |  |  | Project Description: | <Web Crawler>
ID | Current Status | Risk Impact | Probability of Occurrence | Risk Map | Risk Description | Project Impact | Risk Area | Symptoms | Triggers | Risk Response Strategy | Response Strategy | Contingency Plan
1 | Open | High | Medium | Red | Current project skill set may not be adequate to complete all project work. | If required skills are not identified or obtained, project schedule may slip and possibly restrict the accomplishment of project goals. | Schedule | Schedule approaches the required start date with no identification of required skill sets. | Four weeks prior to scheduled start date if no resource is identified with required skill set implement contingency plan. | Mitigation | Find internal resource that meets required skill set or train existing resources on LINUX. | Find resource that meets required skill set through external hiring sources.
2 | Open | High | Medium | Red | A world-wide epidemic "Covid-19" virus causing team members to stay at home while campus is shut down. | We are unable to work together face-to-face with the project. | Schedule | We cannot go to the campus because of the "Stay-at-home" order in effect. | If we do not work on collaborating and seting up meetings, we will not be able to finish the project if no plan is set in advanced. | Mitigation | We try to meet every week and plan a video call meeting. | Use an external application like zoom or whatsapp to meet together online through a video call.
3 | Open | High | Medium | Red | Collaboration Problems with team members. Team members not displaying results. | Not providing results confuses our team and pushes back everyones start time on the work. | Schedule | There is no responses from the people from the group and confusion throughout the project. | Incomplete work and therefore the team will be put off schedule. | Mitigation | We send out a 24 hour notice that if nothing is done, they will be taken out and we will be forced to notify the professor. | Send emails out mentioning they have 24 hours to respond and show results.
4 | Open | Low | Medium | Green | Data that we gather is insuficiant. | We do not have clear results. | Schedule | Our report for analysis will not be as accurate as it could have been. | If our data shows inconsistencies when read or corralated. | Mitigation | Low | We gather more data from a better source or wait for the code to run longer as it's crawling.
5 | Open | High | Low | Yellow | Issues with Security, choosing more than one language. | If our code expands upon more than just python, then there will be more vulnerablities we must account for. | Technical Obsolescence | Some bugs or depricated libraries that we should not have been using. | If someone mentions that they want to go above and beyond, they must state how they will do so and if it's feasible possible with the time we have. | Mitigation | Medium | If we can that would be great with the money that we are given, if we do not have the time with the amount of resources then it is not feasible.
6 | Open | High | Medium | Red | Issues with coding with Python. | If the issues with coding occurs, then we will need an increase of time set upon the schedule for the project. | Schedule | Code doesn't work as intended or might not even run at all; worst case scenario. | If there is an issue, we all must come together to fix the code so that we can finish on time. | Mitigation | High | Work together and get on a call.
7 | Open | High | Low | Yellow | Api data integration, Getting the data. | Not getting the api limits our use with twitter allowing us to only crawl urls. | Technical Obsolescence | Without having the api, there is no analysis for the data. | Make sure that getting the integration takes only but a few days to recieve. | Mitigation | Medium | Make fake accounts to access the api keys.
8 | Open | Low | High | Yellow | Insuficiant funding. | Not enough funding will hurt the member's ability to perform at their best work. | Initial Costs | Lowers moral or energy work performance for the group since they mainly work for compensation. | Map the amount given for each person retrospective with what job assignment they are performing. | Mitigation | High | Either ask for a raise or ask for what is really feasible with the amount offered.
9 | Closed | Low | High | Closed | Merge conflicts on GitHub. | Merge conflicts on Github makes everyone's life harder for the software development team, especially when they have to fix broken code that was pushed. | Technical Obsolescence | Takes more time to fix and sometimes have to decide which code is needed. | Make sure that fixing the merge conflicts take only 1 day at most. | Mitigation | High | Come together to fix the code/ merge conflict so everyone can pull/push the right code.
10 | Open | High | High | Red | Not enough time for the project. | Not having enough time means that the overall finished product will not fully run or will not be as good as what could have been if we did have enough time. | Overall Project Failure | People rushing to push whatever they have done to present. | If deadline is closing in and there is little done. | Mitigation | High | Ask for an extension.
| Closed | Medium | Medium | Closed | hardware issues. | Not being able to connect or have enough hardware recources to work on the plan limits the amount of work we can do for coding and analyzing. | Dependencies/Interoperability | Slow internet or slow resources for the project. | If someone's computer cannot handle the stress put upon it with our work. | Mitigation | Medium | Work with another grouyp member to finish on their hardware/computer.

## DropDown_Elements (hidden)
Risk Area
Schedule
Initial Costs
Life-cycle Costs
Technical Obsolescence
Feasibility
Reliability of Systems
Dependencies/Interoperability
Surety Considerations
Future Procurements
Project Management
Overall Project Failure
Organizational/Change Management
Business
Data/Information
Technology
Strategic
Security
Privacy
Project Resources